New Business Model (NBM) Pilot

Overview

The Springfield Customer Service Office has been selected as the office to pilot the NBM. The purpose of the pilot is to implement the complete (or as near to complete) complement of NBM components into one office, prior to statewide rollout.

This office has been chosen because there is a full complement of Injury Management (IM) and Employer Management (EM) personnel, the office is centrally located and the proximity to Columbus and Dayton present several remote and wireless technology coverage opportunities.

The entire office will participate in piloting the NBM.

Objectives

The pilot objectives are as follows:

- Study and make modifications to IM and EM business strategies; and drive those improvements into NBM processes, procedures and tools;

- Assess the impact of the medical-only claims transition; and validate workload impacts;

- Introduce virtual teaming tools and concepts; and tailor them to the NBM

processes in action;

- Evaluate policy, training (technical and change management), communications (internal and external), human resources and quality procedures and/or plans;

- Integrate MCOs based on Customer Care Group (CCG)/Customer Care Team (CCT) configurations.

Scope

IM

Overview:

The Springfield Customer Service Office provides a testing site to implement, learn and make modifications to customer care and pursuit of settlement strategies and medical-only claims transition into customer service offices. By implementing and ensuring compliance with IM business processes staff will understand and validate NBM workload impacts.

IM pilot examples include:

- Constitution of one or more Customer Care Groups (CCG) and a complete Customer Care Team (CCT);

- Claim Staffing;

- Customer Care Plan (CCP);

- Pursuit of Settlement.

EM

Overview:

The pilot office will execute, evaluate and change the new EM Service Delivery Model (SDM) in order to learn if it is a more efficient and customer friendly approach to reducing the frequency and severity of claims for Ohio's injured workers and employers. The EM SDM will increase employer on-site time, decrease frequency, severity and lag time for employers and increase EM and IM integration.

The office will fully implement the new SDM by achieving complete training of office staff and daily use of the new business processes.

EM pilot examples include:

- Filtering requests from current employer and new employers;

- Prioritization of the requests using designated tools as a guideline; EMS discretion still remains;

- Precision assignment completed by AE2 with EMS supervision;

- Employer Prep done by AA2 using revised prep packet;

- Queue management to ensure customer service timeliness;

- On-site Assessment used by lead consultant;

- Consulting for Impact to develop better relationships between employers and staff;

- 'More on target' Employer Action Plans (EAP);

- Refine discovery letter writing skills;

- Use of Customer Care Plans for their employer policies;

- Employer and injured worker communications;

- The process of Lead Consultant changes will need to be monitored and facilitated.

IT:

Overview

In general, the IT components will be geared toward the creation of a shared workspace (Portal) that features a variety of communication tools. Remote connectivity solutions will allow team members to access that space, information and its tools regardless of their location.

Due to infrastructure limitations, backend system integration will not be provided and very little process automation will be developed (e.g. no FSA processes).  These features are in scope for the “production” version of the IT solutions.

The Springfield Customer Service Office will be involved with user acceptance testing of final NBM products.  Where feasible, office staff will be used as early adopters of production tools as a final test prior to statewide rollout.

Finally, IT prototype solutions will be created using a technique known as Rapid Application Development (RAD).  This is an iterative approach that will produce a solution that will be implemented and continuously improved.

IT pilot examples include:

- Customer Care Team (CCT) Portal Container (the conduit by which NBM IT solutions are accessed);

- Customer Care Plan (CCP);

- Employer Action Plan (EAP);

- Support of CCT creation;

- Support of Customer Care Group (CCG) creation and basic reporting/monitoring;

- Instant Messaging and Presence;

- Virtual meeting capability;

- Remote and wireless technology solutions that allow access to tools and information primarily via the Portal.

Approach

The pilot implementation approach is broken into two parts: Training & Rollout and Feedback & Improvement.  The Feedback & Improvement component will be coordinated with the NBM product development activities to drive pilot experience and improvements into final solutions.

The NBM processes will be implemented as described earlier in the scope section of this document and according to the NBM requirements as they are defined today.

Feedback & Improvement

A key objective of the pilot is to gather feedback and drive improvements into the processes, procedures, and tools of the NBM based upon the pilot experience.

Feedback will be gathered in several ways:

- Executive panel on-site visits;

- Meetings with designated NBM trainees as identified by the Springfield Customer Service Office manager;

- Interaction between IT analysts, business analysts and office personnel to determine whether or not NBM processes lend themselves to collaborative based IT solutions or if designs of IT solutions need rethinking prior to production scale, development and rollout;

- Targeted surveys to pilot office staff; after eight weeks of implementation.